## Budget Summary
Summary Item | Amount (ZAR)
Base estimated cost | 1076000
Contingency reserve (15%) | 161400
Total estimated project budget | 1237400
Estimate type | ROM / indicative planning estimate
Confidence | Low to medium; no actual rates, vendor quotes, named staff or approved procurement details provided.
Exclusions | VAT treatment, production hosting, ERP/mobile/payment/loyalty implementation, ongoing operational support, and any unapproved procurement.
Governance | Validate scope and cost basis; obtain finance/procurement review; baseline only after sponsor approval.

## Budget Estimate
Cost Category | Basis / Assumption | Quantity / Period | Unit Rate (ZAR) | Estimated Cost (ZAR) | Notes
Personnel - Project Manager | 35 person-days; blended indicative rate | 35 days | 4500 | 157500 | Planning estimate; actual internal charge rates unknown.
Personnel - Business Owner / SMEs | 24 person-days combined across owner and users | 24 days | 3000 | 72000 | Participation, requirements, reviews and UAT.
Personnel - Data Analytics | 30 person-days | 30 days | 4000 | 120000 | Technical workstream labor; separate lead/analyst roles may be combined.
Personnel - Data Science | 30 person-days | 30 days | 4500 | 135000 | Technical workstream labor.
Personnel - Machine Learning | 35 person-days | 35 days | 5000 | 175000 | Technical workstream labor.
Personnel - Generative AI | 30 person-days | 30 days | 5000 | 150000 | Technical workstream labor.
Personnel - Governance / QA / Docs / IT | 39 person-days combined | 39 days | 3500 | 136500 | Indicative effort across specialist roles; overlap to be refined.
Software Licences | Incremental licenses only; existing licenses assumed first | 1 allowance | 25000 | 25000 | Provisional allowance; obtain vendor/organization quotes.
Hardware | Existing managed devices assumed; small contingency allowance | 1 allowance | 15000 | 15000 | Only if approved need; no device purchase assumed by default.
Cloud Services | Approved development/test environment, compute/storage/model access | Project allowance | 40000 | 40000 | Set spending caps; costs depend on usage and platform.
Training | Targeted project/tool/AI governance enablement | Project allowance | 20000 | 20000 | Only approved training.
External Services | Specialist/vendor support allowance | Project allowance | 30000 | 30000 | No commitment; require procurement approval.
|  |  | Subtotal | 1076000 | Before contingency
Contingency Reserve | 15% of estimated base cost |  |  | 161400 | Management reserve; release only through approved change/governance process.
TOTAL ESTIMATED BUDGET |  |  |  | 1237400 | Indicative planning estimate only; not a quote, approved budget or funding request.