## Resource Allocaton
Resource / Role | Core Responsibilities | Assigned Activities / Workstream | Indicative Effort (person-days) | Timing | Skills / Access Required | Status / Assumption
Project Sponsor / Steering Committee | Approve charter, scope, gates, budget, escalated changes | Governance, baseline approval, stage gates | 4 | At gates; monthly/exception | Decision authority; business priorities | Role required; named sponsor not supplied
Project Manager | Integrated plan, dependencies, RAID, communications, schedule/cost monitoring, closure | All project activities; coordinate 4 technical workstreams | 35 | Across full project | Planning, facilitation, reporting, change control | Effort estimate; confirm capacity
Business Owner / Product Lead | Confirm business needs, prioritize questions, accept outputs | Requirements, business questions, review/acceptance | 12 | Initiation, requirements, reviews | Retail business knowledge | Named owner unconfirmed
Data Analytics Lead & Analyst(s) | Own analytics workstream outputs; profile/prepare data and build analysis | Data Analytics workstream | 30 | Mid-project execution | SQL/Excel/BI; authorized data access | Technical team is role-based; PM coordinates only
Data Science Lead & Scientist(s) | Own statistical/forecasting analyses and validation | Data Science workstream | 30 | Mid-project execution | Statistics, Python/R, data science | Technical team is role-based
ML Lead & Engineer(s) | Own ML modeling, evaluation and reproducibility | Machine Learning workstream | 35 | Mid-project execution | ML engineering, model validation | Technical team is role-based
Generative AI Lead & Engineer(s) | Own AI use case/prototype, safeguards and evaluation | Generative AI workstream | 30 | Mid-project execution | LLM evaluation, responsible AI, security | Technical team is role-based
Data Owner / Governance & Privacy | Authorize access, classifications, privacy controls, retention | Data access, risk review, release gate | 8 | Before access and at reviews | Data governance, privacy/security | Access approval must be documented
QA / Test Lead | Test strategy, integrated testing, defect triage, evidence | Testing, quality gate | 15 | Testing/release readiness | Test design, defect management | Role and independence to confirm
Documentation / Change Analyst | Maintain versioned docs, decision log, training materials | Documentation and change control | 10 | Throughout; final phase | Technical writing, repository discipline | May be combined with PM role
Infrastructure / IT Support | Provision approved software, hardware, cloud environments | Environment readiness and access | 6 | Early setup and support | IT administration, security | Costs and provision process unconfirmed
Business Users / SMEs | Review outputs, participate in UAT, provide acceptance | Requirements, validation, UAT | 12 | Requirements and testing | Operational process knowledge | Availability needs confirmation

## RACI
Deliverable / Activity | Sponsor | PM | Business Owner | Technical Leads | Data Governance | QA/Test | Business Users
Project baseline approval | A | R | C | C | C | C | I
Integrated schedule / Gantt | I | A/R | C | C | I | C | I
Business requirements / questions | I | C | A/R | C | C | C | C
Data access and privacy approval | I | C | C | I | A/R | C | I
Workstream technical outputs | I | C | C | A/R | C | C | I
Integrated testing / defect closure | I | C | C | R | C | A/R | C
Business acceptance / UAT | A | C | R | C | I | C | R
Change request decision | A | R | C | C | C | C | I
Final presentation and closure | A | R | C | C | I | C | I

## Tools and Assumptions
Category | Proposed Requirement / Allowance | Assumptions / Controls
Software | Approved office suite, project scheduling/spreadsheet tool, version-controlled repository, BI/analytics and coding tools as relevant | Use existing organizational licenses first; do not procure without approval.
Hardware | Existing managed laptops/workstations; secure storage and backup | No new hardware assumed unless capacity/security assessment identifies a need.
Cloud Services | Approved sandbox / compute / storage / model endpoint only if needed | Least privilege, cost limits, data classification and security approval required.
External Services | Specialist support or training only with sponsor approval | No vendor engagement or production deployment assumed.
Allocation basis | Indicative person-days, not approved FTE or timesheets | Refine with named staff, availability, role overlap and workload.
Scope boundary | PM coordinates four tracks; technical work is delivered by designated track teams | No ERP, mobile app, live production deployment, payment gateway or loyalty-system implementation.