## Detailed Schedule
Activity ID | Activity / Milestone | Duration (working days) | Predecessors (FS) | Planned Start | Planned Finish | Assigned Resource / Role | Project Phase | Early Start (day) | Early Finish (day) | Late Start (day) | Late Finish (day) | Total Float (working days) | Critical?
1.1 | Confirm project mandate, sponsor and approval authority | 2 | — | 2026-10-19 | 2026-10-20 | Project Manager | Initiation | 1 | 2 | 1 | 2 | 0 | Yes
1.2 | Hold project kick-off and confirm governance | 1 | 1.1 | 2026-10-21 | 2026-10-21 | Project Manager | Initiation | 3 | 3 | 3 | 3 | 0 | Yes
2.1 | Validate stakeholder register and power-interest ratings | 2 | 1.2 | 2026-10-22 | 2026-10-23 | Project Manager | Stakeholders | 4 | 5 | 13 | 14 | 9 | No
3.1 | Confirm objectives, business questions and requirements | 4 | 1.2 | 2026-10-22 | 2026-10-27 | Project Manager + Business Owner | Scope & Requirements | 4 | 7 | 4 | 7 | 0 | Yes
5.1 | Confirm workstream leads, capacity and resource commitments | 3 | 1.2 | 2026-10-22 | 2026-10-26 | Project Manager + Workstream Leads | Resources | 4 | 6 | 11 | 13 | 7 | No
6.1 | Create initial risk, issue and dependency register | 3 | 1.2 | 2026-10-22 | 2026-10-26 | Project Manager | Risk & Dependencies | 4 | 6 | 36 | 38 | 32 | No
8.1 | Confirm inventory, ownership, access and status of 10 listed assets | 4 | 1.2 | 2026-10-22 | 2026-10-27 | Project Manager + Data Owners | Dataset Coordination | 4 | 7 | 10 | 13 | 6 | No
2.2 | Confirm engagement and communication cadence | 2 | 2.1 | 2026-10-26 | 2026-10-27 | Project Manager | Stakeholders | 6 | 7 | 15 | 16 | 9 | No
3.2 | Confirm in-scope/out-of-scope boundaries and acceptance criteria | 3 | 3.1 | 2026-10-28 | 2026-10-30 | Project Manager + Sponsor | Scope & Requirements | 8 | 10 | 8 | 10 | 0 | Yes
7.1 | Define communication and reporting arrangements | 2 | 2.2 | 2026-10-28 | 2026-10-29 | Project Manager | Communications & Quality | 8 | 9 | 17 | 18 | 9 | No
8.2 | Coordinate business definitions, data questions and issue escalation | 5 | 8.1, 3.1 | 2026-10-28 | 2026-11-03 | Project Manager + Technical Leads | Dataset Coordination | 8 | 12 | 34 | 38 | 26 | No
3.3 | Approve scope baseline | 0 | 3.2 | 2026-11-02 | 2026-10-30 | Sponsor / Approver (TBC) | Milestone | 11 | 10 | 39 | 38 | 28 | No
7.3 | Run recurring status updates and stakeholder communications | 20 | 7.1 | 2026-10-30 | 2026-11-26 | Project Manager | Communications & Quality | 10 | 29 | 19 | 38 | 9 | No
4.1 | Develop detailed schedule and dependency map | 3 | 3.2 | 2026-11-02 | 2026-11-04 | Project Manager | Planning | 11 | 13 | 11 | 13 | 0 | Yes
7.2 | Define project-level quality and review checkpoints | 3 | 3.2 | 2026-11-02 | 2026-11-04 | Project Manager + Workstream Leads | Communications & Quality | 11 | 13 | 21 | 23 | 10 | No
8.3 | Coordinate four workstream plans and cross-workstream dependencies | 5 | 5.1, 4.1, 8.1 | 2026-11-05 | 2026-11-11 | Project Manager + Workstream Leads | Dataset Coordination | 14 | 18 | 14 | 18 | 0 | Yes
7.4 | Track quality reviews and cross-workstream hand-offs | 10 | 7.2, 8.3 | 2026-11-12 | 2026-11-25 | Project Manager + Workstream Leads | Communications & Quality | 19 | 28 | 29 | 38 | 10 | No
8.4 | Monitor workstream progress, blockers, decisions and changes | 20 | 8.3 | 2026-11-12 | 2026-12-09 | Project Manager | Dataset Coordination | 19 | 38 | 19 | 38 | 0 | Yes
9.1 | Coordinate integrated testing plan and readiness checkpoints | 4 | 8.3, 7.2 | 2026-11-12 | 2026-11-17 | Project Manager + Workstream Leads | Reporting & Closure | 19 | 22 | 24 | 27 | 5 | No
9.2 | Coordinate issue resolution, retesting and sign-off evidence | 5 | 9.1 | 2026-11-18 | 2026-11-24 | Workstream Leads; PM tracks | Reporting & Closure | 23 | 27 | 28 | 32 | 5 | No
9.3 | Coordinate final presentation and management review | 3 | 9.2 | 2026-11-25 | 2026-11-27 | Project Manager + Workstream Leads | Reporting & Closure | 28 | 30 | 33 | 35 | 5 | No
9.4 | Coordinate handover, lessons learned and closure report | 3 | 9.3 | 2026-11-30 | 2026-12-02 | Project Manager | Reporting & Closure | 31 | 33 | 36 | 38 | 5 | No
9.5 | Project closure approved | 0 | 9.4 | 2026-12-03 | 2026-12-02 | Sponsor / Approver (TBC) | Milestone | 34 | 33 | 39 | 38 | 5 | No

## Gantt Chart
Activity ID | Activity | Start | Finish | Critical? | 19-Oct | 20-Oct | 21-Oct | 22-Oct | 23-Oct | 26-Oct | 27-Oct | 28-Oct | 29-Oct | 30-Oct | 02-Nov | 03-Nov | 04-Nov | 05-Nov | 06-Nov | 09-Nov | 10-Nov | 11-Nov | 12-Nov | 13-Nov | 16-Nov | 17-Nov | 18-Nov | 19-Nov | 20-Nov | 23-Nov | 24-Nov | 25-Nov | 26-Nov | 27-Nov | 30-Nov | 01-Dec | 02-Dec | 03-Dec | 04-Dec | 07-Dec | 08-Dec | 09-Dec
1.1 | Confirm project mandate, sponsor and approval authority | 2026-10-19 | 2026-10-20 | Yes | bar: 19-Oct to 09-Dec
1.2 | Hold project kick-off and confirm governance | 2026-10-21 | 2026-10-21 | Yes | bar: 21-Oct
2.1 | Validate stakeholder register and power-interest ratings | 2026-10-22 | 2026-10-23 | No | bar: 19-Oct to 09-Dec
3.1 | Confirm objectives, business questions and requirements | 2026-10-22 | 2026-10-27 | Yes | bar: 22-Oct to 27-Oct
5.1 | Confirm workstream leads, capacity and resource commitments | 2026-10-22 | 2026-10-26 | No | bar: 19-Oct to 09-Dec
6.1 | Create initial risk, issue and dependency register | 2026-10-22 | 2026-10-26 | No | bar: 22-Oct to 26-Oct
8.1 | Confirm inventory, ownership, access and status of 10 listed assets | 2026-10-22 | 2026-10-27 | No | bar: 19-Oct to 09-Dec
2.2 | Confirm engagement and communication cadence | 2026-10-26 | 2026-10-27 | No | bar: 26-Oct to 27-Oct
3.2 | Confirm in-scope/out-of-scope boundaries and acceptance criteria | 2026-10-28 | 2026-10-30 | Yes | bar: 19-Oct to 09-Dec
7.1 | Define communication and reporting arrangements | 2026-10-28 | 2026-10-29 | No | bar: 28-Oct to 29-Oct
8.2 | Coordinate business definitions, data questions and issue escalation | 2026-10-28 | 2026-11-03 | No | bar: 19-Oct to 09-Dec
3.3 | Approve scope baseline | 2026-11-02 | 2026-10-30 | No | bar: 02-Nov
7.3 | Run recurring status updates and stakeholder communications | 2026-10-30 | 2026-11-26 | No | bar: 19-Oct to 09-Dec
4.1 | Develop detailed schedule and dependency map | 2026-11-02 | 2026-11-04 | Yes | bar: 02-Nov to 04-Nov
7.2 | Define project-level quality and review checkpoints | 2026-11-02 | 2026-11-04 | No | bar: 19-Oct to 09-Dec
8.3 | Coordinate four workstream plans and cross-workstream dependencies | 2026-11-05 | 2026-11-11 | Yes | bar: 05-Nov to 11-Nov
7.4 | Track quality reviews and cross-workstream hand-offs | 2026-11-12 | 2026-11-25 | No | bar: 19-Oct to 09-Dec
8.4 | Monitor workstream progress, blockers, decisions and changes | 2026-11-12 | 2026-12-09 | Yes | bar: 12-Nov to 09-Dec
9.1 | Coordinate integrated testing plan and readiness checkpoints | 2026-11-12 | 2026-11-17 | No | bar: 19-Oct to 09-Dec
9.2 | Coordinate issue resolution, retesting and sign-off evidence | 2026-11-18 | 2026-11-24 | No | bar: 18-Nov to 24-Nov
9.3 | Coordinate final presentation and management review | 2026-11-25 | 2026-11-27 | No | bar: 19-Oct to 09-Dec
9.4 | Coordinate handover, lessons learned and closure report | 2026-11-30 | 2026-12-02 | No | bar: 30-Nov to 02-Dec
9.5 | Project closure approved | 2026-12-03 | 2026-12-02 | No | bar: 19-Oct to 09-Dec

## Critcal Path
Analysis | Result
Project duration (working days) | 38
Planning start (assumption) | 2026-10-19
Planning finish (assumption) | 2026-12-09
Critical activity IDs | 1.1 → 1.2 → 3.1 → 3.2 → 4.1 → 8.3 → 8.4
Critical activities | Confirm project mandate, sponsor and approval authority; Hold project kick-off and confirm governance; Confirm objectives, business questions and requirements; Confirm in-scope/out-of-scope boundaries and acceptance criteria; Develop detailed schedule and dependency map; Coordinate four workstream plans and cross-workstream dependencies; Monitor workstream progress, blockers, decisions and changes
Method | CPM forward/backward pass; finish-to-start relationships; durations in working days; no resource leveling; no weekends.
Important limitation | Dependency logic and duration estimates are provisional. Validate with sponsor/workstream leads; resource constraints and public holidays are not modeled.

## Milestone
Milestone | Date | Predecessor / Condition | Evidence / Gate
Confirm project mandate, sponsor and approval authority | 2026-10-19 | Start | Sponsor / designated approver sign-off or documented evidence
Approve scope baseline | 2026-11-02 | 3.2 | Sponsor / designated approver sign-off or documented evidence
Project closure approved | 2026-12-03 | 9.4 | Sponsor / designated approver sign-off or documented evidence